## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1.1 | As an Admin I can Create Entity Employee (Admin,Reviewer,Lawyer) | 3 | Ali Souidan
1.2 | As an Admin I can Read Entity Employee (Admin,Reviewer,Lawyer) | 2 | Ali Souidan | 1.1
1.3 | As an Admin I can Update Entity Employee (Admin,Reviewer,Lawyer) | 3 | Ali Souidan | 1.1
1.4 | As an Admin I can Delete Entity Employee (Admin,Reviewer,Lawyer) | 1 | Youssef El Sebaei
1.5 | Test Entity Employee CRUD | 2 | Youssef Sameh | 1.1 | Yes
2 | As an Admin I can CRUD External Entities | 3 | Peter
3.1 | As a Reviewer/Lawyer I can Create comments on a form | 3 | Youssef El Sebaei | 4.2
3.2 | As a Reviewer/Lawyer I can Read comments on a form | 1 | Laithy | 4.2
3.3 | As a Reviewer/Lawyer I can Update comments on a form | 2 | Laithy | 4.2
3.4 | As a Reviewer/Lawyer I can Delete comments on a form | 1 | Youssef El Sebaei | 4.2
3.5 | Test Comments CRUD | 2 | Hussein Badr | 3.1 | Yes
4.1 | As a Lawyer/Investor I can delete my company form | 3 | Youssef Sameh | 4.2
4.2 | As a Lawyer/Investor I can Create a company form | 8 | Lina
4.3 | As a Lawyer/Investor I can Update a company form | 5 | Hussein Badr | 4.2
4.4 | As a Lawyer/Investor I can Read a company form | 1 | Youssef Sameh | 4.2
4.5 | Test CRUD of form | 5 | Abdelrahman El Naka | 4.2 | Yes
5 | As an Investor I can CRUD my information | 5 | Nadeen Amr
5.1 | Testing Investor CRUD | 3 | Ali Souidan | 5 | Yes