## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As an Unregistered User I can view the Homepage | 8 | Naka | Souidan | Nadeen
2 | As an Unregistered User I can view the Register/Login | 8 | Lina | Abougabal | Naka
3 | As an Investor I can View my Companies | 5 | Nadeen Amr | Souidan | Peter
4 | As an Investor/Lawyer I can Fill a Form | 13 | Souidan | Sebaei | Abougabal
5 | As an Investor I can Track my case | 8 | Badr | Nadeen | Souidan
6 | As an Investor I can Pay Form Fees | 3 | Abougabal | Nadeen | Souidan
7 | As an Investor I can Edit my Profile | 8 | Nadeen Amr | Lina | Souidan
8 | As an Admin I can Register Entity Employees | 8 | Abougabal | Lina | Souidan
9 | As a Lawyer/Reviewer I can View my Workspace | 5 | Lina | Souidan | Abougabal
10 | As an Entity Employee I can view all cases and search for them | 5 | Peter | Souidan | Abougabal
11 | As an Entity Employee I can sort cases based on Creation Date or Case Numbers | 5 | Peter | Souidan | Naka
12 | As a Lawyer/Reviewer I can Reserve an unassigned case to later review | 3 | Souidan | Naka | Laithy
13 | As a User I can navigate through a menu | 5 | Sebaei | Lina | Laithy
14 | As a User I can navigate through a footer | 5 | Laithy | Sebaei | Naka
15 | As a User I can View the Contact Us Page | 5 | Laithy | Naka | Badr
16 | As a User I can View the About Us Page | 5 | Sebaei | Naka | Badr
17 | As a Lawyer/Investor I can Edit a rejected form | 8 | Souidan | Lina | Abougabal
18 | As a Lawyer/Reviewer I can Review my reserved Forms | 5 | Lina | Naka | Souidan
19 | As a Lawyer/Reviewer I can leave comments on a reserved Form | 5 | Naka | Souidan | Lina