## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As a User I can Navigate through a Main Menu | 5 | Sebaei | Souidan | Nadeen
2 | As a Lawyer/Reviewer I can view the workspace | 13 | Lina | Abougabal | Naka
3 | As an investor I can track my case status | 5 | Badr | Souidan | Peter
4 | As an investor I can view my companies | 8 | Nadeen Amr | Sebaei | Souidan
5 | As an entity employee I can view a case details | 8 | Naka | Sebaei | Laithy
6 | As a lawyer/reviewer I can review a form | 13 | Souidan | Sebaei | Laithy
7 | As a reviewer/lawyer I can leave comments | 8 | Abougabal | Lina | Nadeen
8 | As a reviewer I can view my reviewed forms | 8 | Peter | Souidan | Lina
9 | As a User I can Navigate through a footer | 5 | Laithy | Souidan | Nadeen
10 | As an Investor I can Pay for my Form (Backend) | 2 | Souidan | Nadeen | Abougabal
11 | As an Investor I can know the cost of my form (Backend) | 3 | Souidan | Nadeen | Abougabal
12 | Heroku Deployment | 2 | Souidan | Nadeen | Abougabal