## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | Investor CRUD JEST Tests | 21 | Nadeen Amr | Souidan | Badr
2 | External Entities CRUD JEST Tests | 13 | Peter | Souidan | Lina
3.1 | Entity Employee Create JEST Tests | 5 | Souidan | Abougabal | Naka
3.2 | Entity Employee Update JEST Tests | 8 | Souidan | Abougabal | Naka
3.3 | Entity Employee Delete JEST Tests | 5 | Badr | Peter | Nadeen
3.4 | Entity Employee Read JEST Tests | 3 | Badr | Peter | Nadeen
4.1 | Forms Create JEST Tests | 8 | Abougabal | Souidan | Nadeen
4.2 | Forms Update JEST Tests | 8 | Lina | Badr | Souidan
4.3 | Forms Read JEST Tests | 3 | Naka | Souidan | Badr
4.4 | Forms Delete JEST Tests | 8 | Naka | Souidan | Badr
5.1 | Comments Create JEST Tests | 5 | Laithy | Naka | Nadeen
5.2 | Comments Read JEST Tests | 3 | Laithy | Abougabal | Nadeen
5.3 | Comments Update JEST Tests | 5 | Sebaei | Souidan | Nadeen
5.4 | Comments Delete JEST Tests | 2 | Sebaei | Souidan | Nadeen
6 | Heroko Deployment | 1 | Souidan | Lina | Nadeen
7 | As an Investor I can choose to have a Lawyer fill my form | 3 | Lina | Sebaei | Naka
8 | As an Investor I can view my forms | 1 | Naka | Sebaei | Naka
9 | As an Investor/Reviewer I can view comment on form | 1 | Abougabal | Abougabal | Badr
10 | As an admin I can assign Lawyer to fill form | 5 | Souidan | Badr | Nadeen
11 | As a Lawyer /Reviewer can review form | 1 | Abougabal | Lina | Naka
12 | As an Investor/Lawyer I can view status of form | 3 | Lina | Abougabal | Badr
13 | As an External Entity I can get Notified | 3 | Peter | Souidan | Nadeen
14 | As a reviewer I can Create comments on a form | 3 | Badr | Lina | Naka
15 | As a reviewer I can view my reviewed forms | 1 | Peter | Souidan | Badr
16 | As a lawyer I can fill a form | 3 | Souidan | Abougabal | Naka